## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date (dd-mm-yyyy) | End Date (dd-mm-yyyy) | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total effort with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type
#1 | FEA_1.1 | Initial selection | Initially the screen should display the option for Login and Registration for Admin,Doctor and Customer | Task 1 | Create a login JSP which is integrated with the spring security . | critical | Shubham Srivastava | 2019-03-11 | 2019-03-13 | 1 | 3 | Done | Homepage availabiity | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 2 | On clicking registration link it will be redirected to the registration forms of Customer,Admin and doctor |  | Shubham Srivastava | 2019-03-14 | 2019-03-15 | 2 | 3 | Done | Homepage availabiity | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 3 | we have created a navigation bar which will redirect to the different registration forms. |  | Vinayak Gupta | 2019-03-11 | 2019-03-13 | 2 | 3 | Done | Homepage availabiity | Scrum Master | Average | critical | New Requirement
| FEA_1.2 | Customer Registration | As a customer when I clicks on the registration link, it should re-direct to registration form. | Task 4 | Create a JSP for customer registration which will have all the necessary fields. | critical | Shivam Goel | 2019-03-11 | 2019-03-14 | 3 | 1 | Done | FEA_1.1 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 5 | On clicking Register button the form validates using JS . |  | Shivam Goel | 2019-03-15 | 2019-03-17 | 2 | 1 | Done | FEA_1.1 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 6 | After validation data is populated into the corresponding database. |  | Saurabh Gidwani | 2019-03-11 | 2019-03-14 | 3 | 1 | Done | FEA_1.1 | Scrum Master | Average | critical | New Requirement
| FEA_1.2 | Customer Registration | As a customer on Clicking 'Submit' should validate the datatype constraints for each field | Task 7 | On submit JS validation is triggered | critical | Shivam Goel | 2019-03-18 | 2019-03-23 | 3 | 1 | Done | FEA_1.1 | Scrum Master | Average | critical | New Requirement
| FEA_1.2 | Customer Registration | As a customer if I am failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task 8 | Add JS functionality to mark the unfilled field as red | critical | Vinayak Gupta | 2019-03-14 | 2019-03-22 | 2 | 3 | Done | FEA_1.1 | Scrum Master | Medium | critical | New Requirement
| FEA_1.2 | Customer Registration | As a Admin i should be able to view the New Customers for registration | Task 9 | Create a JSP page which retrives all the customer present in the database . | Critical | Vinayak Gupta | 2019-03-23 | 2019-03-29 | 2 | 3 | Done | FEA_1.1 | Scrum Master | Average | critical | New Requirement
| FEA_1.3 | Credential Authentication | A registered Customer - is able click 'Login' link, after keying in 'Customer ID' & 'Password' field and get his credentials authenticated with the existing database entry. | Task 10 | On entering 'Customer ID' & 'Password' the connection with the database is established | critical | Shubham Srivastava | 2019-03-16 | 2019-03-23 | 2 | 3 | Done | FEA_1.2 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 11 | Now the 'Customer ID' will be verified from the database if it exists then the encrypted password is and the verified from the existing password in the database. |  | Shubham Srivastava | 2019-03-24 | 2019-03-25 | 2 | 3 | Done | FEA_1.2 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 12 | On successful validation it would be redirected to the respective Dashboard |  | Shivam Goel | 2019-03-24 | 2019-03-25 | 2 | 3 | Done | FEA_1.2 | Scrum Master | Average | critical | New Requirement
| FEA_1.6 | Doctor Registration | As a doctor when I click on the registration link, it should re-direct to registration form. | Task 13 | Create a JSP for doctor registration which will have all the necessary fields. | Critical | Saurabh Gidwani | 2019-03-15 | 2019-03-16 | 3 | 3 | Done | FEA_1.3 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 14 | On clicking Register button the form validates using JS . |  | Shubham Srivastava | 2019-03-25 | 2019-03-26 | 2 | 3 | Done | FEA_1.3 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 15 | After validation data is populated into the corresponding database. |  | Shubham Srivastava | 2019-03-26 | 2019-03-27 | 3 | 3 | Done | FEA_1.3 | Scrum Master | Average | critical | New Requirement
| FEA_1.6 | Doctor Registration | As a doctor on 'Submit' should validate the datatype constraints for each field | Task 16 | On submit JS validation is triggered | critical | Shivam Goel | 2019-03-27 | 2019-03-28 | 3 | 3 | Done | FEA_1.3 | Scrum Master | Average | critical | New Requirement
| FEA_1.6 | Doctor Registration | As a doctor failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task 17 | Add JS functionality to mark the unfilled field as red | Medium | Shivam Goel | 2019-03-25 | 2019-03-26 | 3 | 3 | Done | FEA_1.3 | Scrum Master | Average | Medium | New Requirement
| FEA_1.6 | Doctor Registration | As a admin i should be able to view the New Doctors for registration | Task 18 | Create a JSP page which retrives all the doctor present in the database . | critical | Shivam Goel | 2019-03-28 | 2019-03-29 | 2 | 3 | Done | FEA_1.3 | Scrum Master | Average | critical | New Requirement
| FEA_1.4 | Admin Registration | As a admin when I click on the registration link, it should re-direct to registration form. | Task 19 | Create a JSP for Admin registration which will have all the necessary fields. | critical | Saurabh Gidwani | 2019-03-16 | 2019-03-18 | 1 | 3 | Done | FEA_1.6 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 20 | On clicking Register button the form validates using JS . |  | Saurabh Gidwani | 2019-03-18 | 2019-03-19 | 4 | 3 | Done | FEA_1.6 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 21 | After validation data is populated into the corresponding database. |  | Saurabh Gidwani | 2019-03-19 | 2019-03-20 | 2 | 3 | Done | FEA_1.6 | Scrum Master | Average | critical | New Requirement
| FEA_1.4 | Admin Registration | As a admin on 'Submit' should validate the datatype constraints for each field | Task 22 | On submit JS validation is triggered | critical | Saurabh Gidwani | 2019-03-20 | 2019-03-25 | 3 | 3 | Done | FEA_1.6 | Scrum Master | Average | critical | New Requirement
| FEA_1.4 | Admin Registration | As a admin if I am failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task 23 | Add JS functionality to mark the unfilled field as red | Medium | Saurabh Gidwani | 2019-03-26 | 2019-03-28 | 2 | 3 | Done | FEA_1.6 | Scrum Master | Average | Medium | New Requirement
#2 | FEA_2.1 | Update Medicare Service Details | As a doctor i should be able to update the mandatory fields of the Medicare Service | Task 24 | Create a JSP form displaying previous values of fields Name,Amount and Description | critical | Vinayak Gupta | 2019-04-01 | 2019-04-02 | 3 | 5 | Done | FEA_1.4 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 25 | Send the updated details to Medical service controller class through model attribute service. |  | Shubham Srivastava | 2019-04-01 | 2019-04-02 | 3 | 5 | Done | FEA_1.4 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 26 | Save the model attribute in object of Medical service class and pass it to DAO layer through Service layer for update and save |  | Shivam Goel | 2019-04-01 | 2019-04-02 | 2 | 5 | Done | FEA_1.4 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 27 | Display a message through Javascript on successful submisson of Medical Service details. |  | Saurabh Gidwani | 2019-04-01 | 2019-04-02 | 3 | 3 | Done | FEA_1.4 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 28 | Display/redirect to the JSP page containing all the updated Medical Services |  | Shivam Goel | 2019-04-03 | 2019-04-04 |  | 3 | Done | FEA_1.4 | Scrum Master | Average | critical | New Requirement
| FEA_4.1 | View Medicare Service/ Doctor / Agent details | As a customer on Clicking the View button corresponding Medicare ID, it should list all the details of the Medicare services | Task 29 | Create a JSP page listing all the Medicare Services and a view button corresponding to them | critical | Shubham Srivastava | 2019-04-03 | 2019-04-04 | 2 | 3 | Done | FEA_2.1 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 30 | Create a function in controller layer that will accept the Medicare Service ID provided by view button. |  | Saurabh Gidwani | 2019-04-03 | 2019-04-04 | 3 | 3 | Done | FEA_2.2 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 31 | Function will call a method in service and DAO layer that accepts ID as parameter and return the Medicare Service object, which is then passed as model attribute to the JSP. |  | Saurabh Gidwani | 2019-04-07 | 2019-04-08 | 2 | 3 | Done | FEA_2.3 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 32 | Create a JSP displaying details of Medicare Services in that object. |  | Shivam Goel | 2019-04-07 | 2019-04-08 | 3 | 3 | Done | FEA_2.4 | Scrum Master | Average | critical | New Requirement
| FEA_4.2 | View Medicare Service/ Doctor / Agent details | As a customer on clicking View Doctor, the page should list all the doctors available | Task 33 | On clicking view doctor a function returning list of all the doctors is called | critical | Vinayak Gupta | 2019-04-07 | 2019-04-08 | 4 | 3 | Done | FEA_2.5 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 34 | The return list of doctors is added as a attribute and is passed to the JSP. |  | Shubham Srivastava | 2019-04-07 | 2019-04-08 | 2 | 3 | Done | FEA_2.6 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 35 | Create a JSP displaying list of all available Doctors. |  | Shivam Goel | 2019-04-08 | 2019-04-09 | 1 | 3 | Done | FEA_2.7 | Scrum Master | Average | critical | New Requirement
| FEA_4.2 | View Medicare Service/ Doctor / Agent details | By Clicking the Doctor Id, it should display all the details of the doctor | Task 36 | Create a function in controller layer that will accept the Doctor ID provided by view button. |  | Shubham Srivastava | 2019-04-08 | 2019-04-09 | 2 | 3 | Done | FEA_2.8 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 37 | Function will call a method in service and DAO layer that accepts ID as parameter and return theDoctor object, which is then passed as model attribute to the JSP. |  | Shivam Goel | 2019-04-09 | 2019-04-10 | 3 | 3 | Done | FEA_2.9 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 38 | Create a JSP displaying details of Doctor in that object. | critical | Vinayak Gupta | 2019-04-09 | 2019-04-10 | 4 | 3 | Done | FEA_4.2 | Scrum Master | Average | critical | New Requirement
| FEA_5.1 | Raise Checkup request | As a customer when I Click on Raise Checkup request link, it should redirect to the Request creation page | Task 39 | Create a JSP form for getting the checkup request | Critical | Saurabh Gidwani | 2019-04-10 | 2019-04-11 | 4 | 5 | Done | FEA_4.3 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 40 | On clicking the Request link a JSP form appears . |  | Shubham Srivastava | 2019-04-07 | 2019-04-08 | 2 | 5 | Done | FEA_4.4 | Scrum Master | Average | critical | New Requirement
| FEA_5.1 | Raise Checkup request | As a customer i should be able to fill in the necessary fields, select date, doctor and Medicare service and submit the request | Task 41 | On clicking the Raise request, a request associated to a particular doctor is created and saved in the corresponding database. |  | Shivam Goel | 2019-04-10 | 2019-04-11 | 3 | 5 | Done | FEA_4.5 | Scrum Master | Average | critical | New Requirement
| FEA_5.1 | Raise Checkup request | As a doctor i should be able to view the Checkup request and approve it | Task 42 | create a request section where doctor is able to view the pending request from the customers. | critical | Vinayak Gupta | 2019-04-10 | 2019-04-11 | 2 | 5 | Done | FEA_4.6 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 43 | On clicking the decline request button it hits the request controller which initiates the decline request method changes the status from the pending to rejected |  | Saurabh Gidwani | 2019-04-10 | 2019-04-11 | 3 | 5 | Done |  | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 44 | On clicking the accept request button it hits the request controller which initiates the accept request method changes the status from the pending to accepted |  | Shubham Srivastava | 2019-04-10 | 2019-04-11 | 3 | 5 | Done |  | Scrum Master | Average | critical | New Requirement
| FEA_6.1 | Update Test results | As a doctor on clicking the Checkup request ID, Doctor should have the option to update the test results | Task 45 | On clicking the update result doctor controller initiates the update result method which returns the update JSP form. | critical | Shivam Goel | 2019-04-07 | 2019-04-08 | 3 | 3 | Done | FEA_5.1 | Scrum Master | Average | critical | New Requirement
|  |  |  | Task 46 | On clicking the save update report button it initiates the method save reports which saves the data into the database and redirect us to the reports JSP. |  | Vinayak Gupta | 2019-04-07 | 2019-04-08 | 3 | 3 | Done | FEA_5.2 | Scrum Master | Average | critical | New Requirement
| FEA_7.1 | View test results | As a customer on clicking the Checkup request ID, Doctor / consumer should be able to view the test results | Task 47 | on clicking the view reports all the reports of corresponding customer/doctor will be displayed in tabular form. | Critical | Shivam Goel | 2019-04-10 | 2019-04-11 | 4 | 3 | Done | FEA_7.1 | Scrum Master | Average | critical | New Requirement
| FEA_8.1 | Admin/Customer/Doctor log off | Option to log off from the system. | Task 48 | when we click logout button which hits the login controller which initiates the logout method and redirect us to the login page. |  | Saurabh Gidwani | 2019-04-10 | 2019-04-11 | 2 | 3 | Done |  | Scrum Master | Average | critical | New Requirement
Shubham Srivastava
Saurabh Gidwani
Shivam Goel
Vinayak Gupta